## Slide 1
Cyber Incident Response Readiness
Assessment results and 90-day action plan
Sample Organization (illustrative) · Financial Services
Assessed January 15, 2026 · Prepared by Sample data — not a real assessment

## Slide 2
EXECUTIVE SUMMARY
Overall maturity band is an application convention applied to the average score (1.00–1.49 Manual, 1.50–2.49 Orchestrated, 2.50–3.49 Proactive, 3.50–4.00 Adaptive). The source maturity model defines levels per dimension only; each dimension progresses independently.
OVERALL MATURITY
L2 Orchestrated
Average 1.80 of 4
PRIORITY GAPS
4
Dimensions at Level 1–2
PLANNED ACTIONS
5
4 high priority
Top priorities
Cross-Functional Coordination (L1) — Write playbooks that assign repeatable actions to security, IT, legal, privacy, communications, and executives.
Documentation & Continuous Improvement (L1) — Centralize incident records so facts, evidence, actions, and decisions are captured in one place.
Incident Execution & Accountability (L2) — Introduce context-based rules so ownership and escalation adjust automatically with incident type, data involved, and impact.
Executive asks
Require each function to name primary and backup responders.
Designate the authoritative incident system of record.
Agree escalation SLAs and the leadership audience for each severity.
Approve notification templates and the sign-off chain for disclosures.

## Slide 3
MATURITY BY DIMENSION
Filled = current level · outlined = target level
Incident Execution & Accountability
1 · Manual
2 · Orchestrated
3 · Proactive
4 · Adaptive
2 → 3
Cross-Functional Coordination
1 → 2
Regulatory & Legal Readiness
2 → 3
Documentation & Continuous Improvement
1 → 2
Training & Operational Readiness
3 → 4

## Slide 4
FINDINGS — WEAKEST FIRST
Dimension | Level | Risk | Next step
Cross-Functional Coordination | L1 Manual | Coordinating through meetings, email, and disconnected channels slows approvals and leaves functions unsure what is expected of them. | Write playbooks that assign repeatable actions to security, IT, legal, privacy, communications, and executives.
Documentation & Continuous Improvement | L1 Manual | Incomplete records and after-the-fact timeline reconstruction leave gaps when decisions must be explained to regulators, auditors, or the board. | Centralize incident records so facts, evidence, actions, and decisions are captured in one place.
Incident Execution & Accountability | L2 Orchestrated | Without defined owners and severity tiers, decisions depend on whoever is available and escalations happen late or not at all. | Introduce context-based rules so ownership and escalation adjust automatically with incident type, data involved, and impact.
Regulatory & Legal Readiness | L2 Orchestrated | Manual legal interpretation can miss thresholds or deadlines, increasing regulatory and contractual exposure. | Trigger draft notices automatically from incident facts and the applicable regulatory requirements.
Training & Operational Readiness | L3 Proactive | Static, security-only playbooks that are rarely exercised fail in ways that only surface during a real incident. | Run realistic, on-demand exercise scenarios, including AI-generated scenarios, so teams build muscle memory.

## Slide 5
90-DAY PLAN · DAYS 1–30
Establish incident ownership, severity, and cross-functional responsibilities; set owners and measures.
Priority | Action | Dimension | Owner | Due | Acceptance criteria
High | Write playbooks that assign repeatable actions to security, IT, legal, privacy, communications, and executives. | Cross-Functional Coordination → L2 | Incident Response Lead | 2026-02-14 | Each function has reviewed and accepted its responsibilities in the playbooks.
High | Centralize incident records so facts, evidence, actions, and decisions are captured in one place. | Documentation & Continuous Improvement → L2 | Incident Response Lead with Legal | 2026-02-14 | All incidents in the review period have records in the central repository.
High | Introduce context-based rules so ownership and escalation adjust automatically with incident type, data involved, and impact. | Incident Execution & Accountability → L3 | CISO / Incident Response Lead | 2026-02-14 | Escalations in an exercise or live incident follow the rule set within the SLA.

## Slide 6
90-DAY PLAN · DAYS 31–60
Map regulatory obligations and stand up a single system of record for the response.
Priority | Action | Dimension | Owner | Due | Acceptance criteria
High | Trigger draft notices automatically from incident facts and the applicable regulatory requirements. | Regulatory & Legal Readiness → L3 | General Counsel / Privacy Counsel | 2026-03-16 | In an exercise, applicable obligations and draft notices are produced from incident facts.

## Slide 7
90-DAY PLAN · DAYS 61–90
Run a cross-functional exercise, measure outcomes, and feed findings back into playbooks.
Priority | Action | Dimension | Owner | Due | Acceptance criteria
Medium | Run realistic, on-demand exercise scenarios, including AI-generated scenarios, so teams build muscle memory. | Training & Operational Readiness → L4 | Incident Response Lead / Exercise Coordinator | 2026-04-15 | Exercises per quarter and playbook update rate are tracked and reviewed by leadership.

## Slide 8
MEASURES OF SUCCESS
Incident Execution & Accountability: % of incidents opened with an owner and severity assigned; escalation SLA adherence.
Cross-Functional Coordination: % of incidents with documented cross-functional tasks and approvals; stakeholder response time.
Regulatory & Legal Readiness: % of incidents with obligations mapped; time to produce a notification timeline.
Documentation & Continuous Improvement: % of incidents with a complete timeline and evidence package; time to generate a final report.
Training & Operational Readiness: # of exercises per quarter; % of playbooks updated after incidents and exercises.
This report reflects self-reported answers against the BreachRx Cyber Incident Response Management (CIRM) Maturity Model. Recommendations are planning guidance, not legal advice, and do not guarantee incident outcomes, privilege, or regulatory compliance.
Optional BreachRx capabilities are shown for reference only and are separate from the neutral recommendations. They do not assure legal privilege, regulatory compliance, or incident preparedness. Confirm current feature availability before relying on it.
Model cirm-2026.1 · Rules cirm-rules-2026.1